## Sheet1
The Product Backlog is your ultimate 'to-do list' for your project. Update this as you go.
At the beginning of the sprint, drag the user stories that you will be working on for that sprint, under the appropriate sprint heading.
Sprint 1
ID | User Story | Estimation (XS-XL) | Priority (low-high) | Task Owner | Status | Notes
1 | Route
1.1 | Web App has a [layout page which has functioning navbar] that all [routes] will inherit from | XL | High | Syed Talha Ali | Completed
1.2 | Web app has a [route] to [home page] | M | High | Syed Talha Ali | Completed
1.3 | Web app has a [route] to [about page] | S | Low | Syed Talha Ali | Pending
1.4 | Web app has a [route] to [contact page] | M | Low | Syed Talha Ali | Pending
1.5 | Web app has a [route] to [features page] | S | Low | Syed Talha Ali | Pending
1.6 | Web app has a [route] to [examples page] | S | Low | Syed Talha Ali | Pending
1.7 | Web app has a [route] to a [sign up page] | L | High | Syed Talha Ali | Completed
1.8 | Web app has a [route] to a [log in page] | L | High | Syed Talha Ali | Completed
2 | User Class Model
2.1 | As a [user], I want to have [a unique id, username, email and password] (ADD DATE LATER and GRAPHS CREATED and VIDEOS)] | M | High | Syed Talha Ali | Pending
2.2 | As a [user], I can [view stats such as the total graphs created and date account was created] | S | Low | Syed Talha Ali | Pending
2.3 | As a [user] I can [create graphs] | XL | High | Syed Talha Ali | Pending
2.4 | As a [user] I can [save created graphs] | M | High | Syed Talha Ali | Pending
2.5 | As a [user] I can [delete saved graphs] | M | High | Syed Talha Ali | Pending
3 | Forms
3.1 | Web App has a [registration form] for [sign up page] | M | High | Syed Talha Ali | Completed
3.2 | Web app has a [log in form] for [log in page] | M | High | Syed Talha Ali | Completed
4 | Database
4.1 | Web app has a functioning [database] that will store [User] and [Graph] information | S | High | Syed Taha Ali | Completed
4.2 | [Database] can store [User] and [Graph] information | M | High | Syed Taha Ali | Pending
Sprint 2
1 | Route
1.3 | Web app has a [route] to [about page] | S | Low | Syed Talha Ali | Pending
1.4 | Web app has a [route] to [contact page] | M | Low | Syed Talha Ali | Pending
1.5 | Web app has a [route] to [features page] | S | Low | Syed Talha Ali | Pending
1.6 | Web app has a [route] to [examples page] | S | Low | Syed Talha Ali | Pending
1.9 | Web app has a [route] to [choose page] where the [user] chooses a [graph] | M | High | Syed Talha Ali | Completed
1.11 | Web app has a [route] to [Create graph page] where the [user] creates a [graph] | L | High | Syed Talha Ali | Completed
2 | User Class Model
2.1 | As a [user], I want to have [a unique id, username, email and password] (ADD DATE LATER and GRAPHS CREATED and VIDEOS)] | M | High | Syed Talha Ali | Completed
2.2 | As a [user], I can [view stats such as the total graphs created and date account was created] | S | Low | Syed Talha Ali | Completed
2.3 | As a [user] I can [create graphs] | XL | High | Syed Talha Ali | Completed
2.4 | As a [user] I can [save created graphs] | M | High | Syed Talha Ali | Completed
2.5 | As a [user] I can [delete saved graphs] | M | High | Syed Talha Ali | Pending
3 | Forms
3.2 | Web App has a [create bar graph form] for [create graph page] | M | High | Syed Taha Ali | Completed
3.3 | Web App has a [create graph nonbar form (for other types of graphs)] for [create graph page] | M | High | Syed Talha Ali | Completed
3.4 | Web App has a [save graph form] | M | High | Syed Talha Ali | Completed
3.5 | Web App has a [delete graph form] | M | High | Syed Taha Ali | Pending
4 | Database
4.2 | [Database] can store [User] and [Graph] information | M | High | Syed Talha Ali | Completed
5 | Graph Class Model (video)
5.1 | A [graph] has a [unique id] | M | High | Syed Taha Ali | Completed
5.2 | A [graph] has a [html code], that allows [users] to embed the [graph] on their personal websites | M | High | Syed Taha Ali | Completed
5.3 | A [graph] has an author [user] | M | High | Syed Taha Ali | Completed
Sprint 3
1 | Route
1.3 | Web app has a [route] to [about page] | S | Low | Syed Talha Ali | Pending
1.4 | Web app has a [route] to [contact page] | M | Low | Syed Talha Ali | Completed
1.5 | Web app has a [route] to [features page] | S | Low | Syed Talha Ali | Pending
1.6 | Web app has a [route] to [examples page] | S | Low | Syed Talha Ali | Pending
1.12 | Web app has a [route] to [profile page] | XL | High | Syed Talha Ali | Completed
1.13 | Web app has a [route] to [graph page] (video page) | M | High | Syed Talha Ali | Completed
1.14 | [routes] restricted to [User-only pages] | S | High | Syed Talha Ali | Completed
1.15 | Each page has User stats box on left side if user is logged in otherwise a daily news page. | M | Low | Syed Talha Ali | Completed
2 | User Class Model
2.5 | As a [user] I can [delete saved graphs] | M | High | Syed Taha Ali | Completed
2.6 | As a [user] I can [log out] | S | High | Syed Taha Ali | Completed
3 | Forms
3.5 | Web App has a [delete graph form] | M | High | Syed Talha Ali | Completed
3.6 | Web App has a [contact form] for [contact page] | M | Low | Syed Talha Ali | Completed
6 | Profile Page
6.1 | Profile Page has [route] to [choose graph page] | S | High | Syed Taha Ali | Completed
6.2 | [user] can view saved [graphs] | M | High | Syed Talha Ali | Completed
6.3 | [user] can delete saved [graphs] | M | High | Syed Talha Ali | Completed
6.4 | [user] can view advanced info about [graphs] (Html code) | M | High | Syed Talha Ali | Completed
Sprint 4
1 | Route
1.3 | Web app has a [route] to [about page] | S | Low | Syed Talha Ali | Completed
1.5 | Web app has a [route] to [features page] | S | Low | Syed Talha Ali | Completed
1.6 | Web app has a [route] to [examples page] | S | Low | Syed Talha Ali | Completed
7 | CSS/Styling
7.1 | Each page is made more aesthetically pleasing | L | High | Syed Talha Ali | Completed
8 | Additional Features/Errors
8.1 | Fix excel document format error | M | High | Syed Talha Ali | Completed
8.2 | [User] can change [email and password] | M | Low | Syed Talha Ali | Pending
8.3 | [User] can add line of best fit on each graph | M | Low | Syed Taha Ali | Pending